## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Group 1 Communications |  |  |  |  | COMPANY NAME | [8 empty] | Group 1 Communications
| PROJECT MANAGER | Ayoub |  |  |  |  | DATE | [8 empty] | 2024-10-27
[7 empty] | PHASE Init() | [14 empty] | PHASE Requirements | [19 empty] | PHASE Design | [19 empty] | PHASE Testing/Implementation
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Init()
1.1.1 | Create Group Presentation Slide | Ayoub Mekkaoui | 2024-08-22 | 2024-09-05 |  | 100% | bar: WEEK 1 R to WEEK 3 R
2 | Requirements |  | 2024-09-05 | 2024-10-03
2.1 | Created SRS “Skeleton” | GROUP | 2024-09-05 | 2024-09-12 | 7 | 100% | bar: WEEK 1 R to WEEK 4 R
2.2 | Create Github Repo for Project | GROUP | 2024-09-05 | 2024-09-14 | 9 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote Purpose(1.1,1.2,1.3) | GROUP | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote General Description(2.1-2.5) | GROUP | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote 5 Log-In Requirements (3.1.4.1 to 3.1.4.5) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote 10 GUI Requirements (3.1.8.1 to 3.1.8.10) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote 4 External Interface Requirements (3.2.1 to 3.2.4) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote 3 Internal Interface Requirements (3.3.1 to 3.3.3) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Wrote 7 Non-Functional Requirements in 4.1, 4.2, 4.3 | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Created Use Case #1 UML | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Drew Use Case Diagram #1 (Ms Paint) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
2.3 | Added reqs to 3.1.1-3.1.3, 3.1.5, 3.1.6 | Ben Levy | 2024-09-05 | 2024-09-15 | 10 | 100% | bar: WEEK 1 R to WEEK 4 F
| Added reqs to 3.1.1.3, 3.1.1.4 | Van Nguyen | 2024-09-05 | 2024-09-26 | 21 | 100% | bar: WEEK 1 R to WEEK 6 R
| Wrote 5 reqs 3.1.7.1-3.1.7.4 | Ayoub Mekkaoui | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Wrote 3 reqs 3.1.8.1-3.1.8.3 | Ayoub Mekkaoui | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added 3 Use Cases (ID: 002, 003, 004) | Ayoub Mekkaoui | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added 3 reqs to Security and Privacy and edited 3.1.5.1 | Ben Levy | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Updated document outline(no visible changes) | Ben Levy | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added use case “Create User” | Ben Levy | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Reformatted document | Ben Levy | 2024-09-05 | 2024-09-28 | 23 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added reqs to User Reqs 3.1.5.3-3.1.5.5, 3.1.6.3- 3.1.6.5 | Van Nguyen | 2024-09-05 | 2024-09-19 | 14 | 100% | bar: WEEK 1 R to WEEK 5 R
| Fix requirement for Common Req at 3.1.1.4 | Van Nguyen | 2024-09-05 | 2024-09-19 | 14 | 100% | bar: WEEK 1 R to WEEK 5 R
| Added 3 use cases(ID: 006, 007,008) | Van Nguyen | 2024-09-05 | 2024-09-19 | 14 | 100% | bar: WEEK 1 R to WEEK 5 R
| Wrote reqs 3.1.5.5 & 3.1.6.8, Added Use Cases (ID:012, 13) | Ibraheem Fawal | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Class Diagram | Ayoub Mekkaoui | 2024-09-29 | 2024-09-29 | 0 | 100% | bar: WEEK 6 F
| Added use cases “Delete User” and “View Logs” | Ben Levy | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added sequence diagram for “Create User” | Ben Levy | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Fixed Product Architecture | Akbar Hashimi | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Requirement 3.1.8.4 | Akbar Hashimi | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Requirement 3.1.5.6 | Akbar Hashimi | 2024-09-05 | 2024-09-29 | 24 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Requirement 4.1.2 | Akbar Hashimi | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Edited Use Case 10 | Akbar Hashimi | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Requirement 3.1.6.7 | Akbar Hashimi | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Use Case 11 | Akbar Hashimi | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Sequence Diagram for Use Case ID: 001 and ID: 002 | Ayoub Mekkaoui | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Sequence Diagram for “Delete User” and “View Logs” | Ben Levy | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Use Cases (ID: 014 - 017) and left comments for review | Ibraheem Fawal | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Use Case Diagram(ID: 006, 007) | Van Nguyen | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Updated Use case 006 and revised Use Case 007 | Van Nguyen | 2024-09-05 | 2024-09-30 | 25 | 100% | bar: WEEK 1 R to WEEK 6 F
| Added Use Case 018, added Sequence Diagram (012 - 013) | Ibraheem Fawal | 2024-09-05 | 2024-10-01 | 26 | 100% | bar: WEEK 1 R to WEEK 7 T
| Added Requirement 3.1.5.7 | Akbar Hashimi | 2024-09-05 | 2024-10-01 | 26 | 100% | bar: WEEK 1 R to WEEK 7 T
| Updated Class Diagram | Ayoub Mekkaoui | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Added Sequence Diagram for Use Case ID: 003 and ID: 004 | Ayoub Mekkaoui | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Added Use Cases 019, 020, 021 | Nico Palma | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Added Requirements 3.1.7.5, 3.1.7.6 & 3.1.9.11 | Nico Palma | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Removed Use Case 13 | Akbar Hashimi | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Add Admin Use Case Diagram | Van Nguyen | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Added User Use Case Diagram | Akbar Hashimi | 2024-09-29 | 2024-10-02 | 3 | 100% | bar: WEEK 6 F to WEEK 7 W
| Added Sequence Diagram for Use Case 11 | Akbar Hashimi | 2024-09-29 | 2024-10-03 | 4 | 100% | bar: WEEK 6 F to WEEK 7 R
| Added Sequence Diagram (ID: 014 and 017) | Ibraheem Fawal | 2024-09-29 | 2024-10-03 | 4 | 100% | bar: WEEK 6 F to WEEK 7 R
| Created Trello | Van Nguyen | 2024-09-29 | 2024-09-29 | 0 | 100% | bar: WEEK 6 F
3 | Design |  | 2024-10-04 | 2024-10-31
3.1 | UML candidate for MessageHandler, Message, Group | Ayoub Mekkaoui | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
3.2 | UML candidate for User Module | Akbar Hashimi | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
3.2.1 | UML candidate for Storage Manager | Ibraheem Fawal | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
3.2.2 | UML candidate for Log In, Authentication | Van Nguyen | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
3.3 | UML candidate for Admin | Nico Palma | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
| Added Requirement 3.1.5.8 | Akbar Hashimi | 2024-10-08 | 2024-10-13 | 5 | 100% | bar: WEEK 8 T to WEEK 8 F
| Added Sequence Diagram for Use Case 18 and 19 | Nico Palma | 2024-10-08 | 2024-10-14 | 6 | 100% | bar: WEEK 8 T to WEEK 9 M
| Removed old table of contents | Ben Levy | 2024-10-08 | 2024-10-15 | 7 | 100% | bar: WEEK 8 T to WEEK 9 T
| Created Client Side Class Diagram | Ayoub Mekkaoui | 2024-10-08 | 2024-10-18 | 10 | 100% | bar: WEEK 8 T to WEEK 9 F
| Created Classes UserData, ClientMessage, MessageType | Ayoub Mekkaoui | 2024-10-08 | 2024-10-18 | 10 | 100% | bar: WEEK 8 T to WEEK 9 F
| Created Class ChatBox | Ayoub Mekkaoui | 2024-10-08 | 2024-10-18 | 10 | 100% | bar: WEEK 8 T to WEEK 9 F
| Updated full Class Diagram & attributes/methods for all | Ayoub Mekkaoui | 2024-10-08 | 2024-10-18 | 10 | 100% | bar: WEEK 8 T to WEEK 9 F
| Added Use Case 021 - 026 | Ibraheem Fawal | 2024-10-08 | 2024-10-25 | 17 | 100% | bar: WEEK 8 T to WEEK 10 F
| UseCase 027, removed UC 025, finished UC 021-027 descriptions | Ibraheem Fawal | 2024-10-08 | 2024-10-26 | 18 | 100% | bar: WEEK 8 T to WEEK 10 F
| Add 3.1.6.9 and 3.1.6.9 to Admin Module requirement | Van Nguyen | 2024-10-08 | 2024-10-28 | 20 | 100% | bar: WEEK 8 T to WEEK 11 M
| Added Use Case and sequence diagram for ID: 028, 029 | Van Nguyen | 2024-10-08 | 2024-10-29 | 21 | 100% | bar: WEEK 8 T to WEEK 11 T
| Made changes to Class Diagram Client Side | Ayoub Mekkaoui | 2024-10-08 | 2024-10-29 | 21 | 100% | bar: WEEK 8 T to WEEK 11 T
| Updated Sequence Diagrams 12 & 13 | Ibraheem Fawal | 2024-10-08 | 2024-10-29 | 21 | 100% | bar: WEEK 8 T to WEEK 11 T
| Create Relationships in Class Diagram | Akbar Hashimi | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Updated User Use Case Diagram | Akbar Hashimi | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Updated Admin Use Case Diagram | Van Nguyen | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Updated Seq Diagrams 14 & 17, Added Seq Diagrams 21 - 27 | Ibraheem Fawal | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Removed Use Case & Sequence Diagram 022 | Ibraheem Fawal | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Created Use Case Diagram ID: 30, 31 | Ayoub Mekkaoui | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Created Sequence Diagram ID: 30, 31 | Ayoub Mekkaoui | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Created Req 3.1.5.10 | Akbar Hashimi | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
| Removed UC 16 & 20, Updated Seq Diagrams 12-14, 23, 24, 26, 27 | Ibraheem Fawal | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
3.3.1 | Update Use case and Seq Diagram ID:007 | Van Nguyen | 2024-10-30 | 2024-10-31 | 0 | 100% | bar: WEEK 11 W to WEEK 11 R
4 | Implementation
| Make Connection Test and Basic Client Handler Test | Akbar Hashimi | 2024-10-31 | 2024-11-08 | 8 | 0% | bar: WEEK 11 R to WEEK 12 F
4.2 | Make Basic GUI Elements and test | Akbar Hashimi, Ben Levy | 2024-11-09 | 2024-11-13 | 4 | 0% | bar: WEEK 12 F to WEEK 13 W
4.3 | Connection to GUI and Client Tested and Complete | Akbar Hashimi, Ben Levy, Ibraheem Fawal | 2024-11-13 | 2024-11-20 | 7 | 100% | bar: WEEK 13 W to WEEK 14 W
| Login GUI w/ Username, Password, and Server IP and Port | Ibraheem Fawal | 2024-11-06 | 2024-11-19 | 13 | 0% | bar: WEEK 12 W to WEEK 12 F
| ClientSender, Client Receive Skeleton made (server-side code) | Van Nguyen | 2024-11-14 | 2024-11-16 | 2 | 100% | bar: WEEK 13 R to WEEK 13 F
| ClientProcess skeleton (server-side code) | Akbar | 2024-11-14 | 2024-11-16 | 2 | 100% | bar: WEEK 13 R to WEEK 13 F
| Submit V1 of the class server diagram | Akbar | 2024-11-17 | 2024-11-17 | 0 | 100% | bar: WEEK 13 F
| Complete Admin | Van Nguyen | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complet User | Van Nguyen | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Authentication System | Ayoub Mekkaoui | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete ChatBox | Ayoub Mekkaoui | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Message Handler | Ayoub Mekkaoui | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Storage Manager | Ayoub Mekkaoui | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Server and Client Handler | Ayoub / Ben | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Message Interface/Classes | Ben | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete Client Class | Ayoub / Ben | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T
| Complete GUI | Akbar Hashimi / Ben Levy / Ayoub | 2024-10-31 | 2024-11-19 | 19 | 100% | bar: WEEK 11 R to WEEK 16 T

## Try Smartsheet
Try Smartsheet for Free